GREASE - REHEARSAL SCHEDULE

|  | Monday | Tuesday | Wednesday | Thursday | Friday | Weekend |
| --- | --- | --- | --- | --- | --- | --- |
| Week 6 9-13 March |  | Blocking pg 15-18 and 23-30 |  | Music and Dancing rehearsal – ALL |  | Run Pg 7-30 Speaking parts |
| Week 7 16-20 March |  | Blocking pg 31-34, then 23-34 |  | Prom scene dancing and music - ALL |  | Run blocking ACT ONE |
| Week 8 23-27 March |  | Blocking pg 37-42 words only |  | Blocking pg 43-47 ALL – Dancing and singing |  | Run blocking pg 37-47 Blocking 48 and 49 |
| Week 9 30-3 April |  | Blocking pg 51-59 |  | Prom scene dancing and music - ALL |  | Run blocking ACT TWO |
| Week 10 6-8th April | BOOKS DOWN | Bits and pieces TBA |  |  |  |  |
| Holidays – Week One | No rehearsals |  |  |  |  | No rehearsals |
| Holidays – Week Two |  | Run ACT ONE with music and dancing 1000 - 1600 |  | Run ACT TWO with music and dancing 1000-1600 |  | Run whole show (Piano only) |
| Term 2, Week 1 27-1 May |  | Full run Dress rehearsal |  | Full run Dress rehearsal |  | Full run Dress rehearsal |
| Week 2 4-8 May | Pack In | Technical run | Final dress tech |  | Opening Night |  |
| Week 3 11-15 May | No show |  |  |  | Closing Night |  |